## Report
Gateau au yahourt
Earned Value Analysis Report
Planned Value (PV)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Trouver recette du gateeau au yahourt | 1 |  |  | 1
2 | Identifier les ingredients et les materiels necessaires | 1 |  |  |  | 1
3 | Acheter les ingredients et les materiels necessaires | 1 |  |  |  |  | 1
4 | Realiser le gateau au yahourt | 2 | [5 empty] | 2
0
0
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 5 | 0 | 0 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Planned Value (PV) | 0 | 0 | 1 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 30 | 35
|  | Cumulative Earned Value (EV) | 0 | 0 | 0 | 1.5 | 1.9 | 2.8 | 5
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
Cumulative Earned Value (EV)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Trouver recette du gateeau au yahourt | 1 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | Identifier les ingredients et les materiels necessaires | 1 |  |  |  | 50% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | Acheter les ingredients et les materiels necessaires | 1 | [5 empty] | 80% | 100% | 100% | 100% | 100% | 100% | 100%
4 | Realiser le gateau au yahourt | 2 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 0 | 0 | 0 | 1.5 | 1.9 | 2.8 | 5 | 5 | 5 | 5 | 5 | 5

## AC
Actual Cost Worksheet
Actual Cost (AC) of Work Performed
WBS | Task Name |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Trouver recette du gateeau au yahourt
2 | Identifier les ingredients et les materiels necessaires
3 | Acheter les ingredients et les materiels necessaires |  | 6: 30; 7: 5
4 | Realiser le gateau au yahourt
- | -
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 0 | 0 | 0 | 0 | 0 | 30 | 5 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 0 | 0 | 0 | 0 | 0 | 30 | 35 | 35 | 35 | 35 | 35 | 35

## Rules
Impact Chiffres
1 | Lendemain de fête: non productif
2 | Journée banale: production classique
3 | Red Bull donne des ailes: production double
4 | Risque +1
5 | Journée banale: production classique
6 | Erreur de debutant : production arriere
Qui \ Tours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
XXX
YYY
ZZZ
Risques: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Pluie ( probaa: 10)
QQQ
FFF
GGG